## NELSIP Deployment Plan_
NELSIP 2026/2029 Deployment Plan
R | Responsible - the person or team who does the activity and completes the work.
A | Accountable - the person or team who owns the activity and is ultimately answerable for the outcome.
C | Consulted - the people or teams who give input, advice, or expertise before action is taken.
I | Informed - the people or teams who need to be kept updated on progress or decisions.
Note: This master deployment plan will be broken down into Sector Specific Deployment plans. Specific lead organisation(s) will be agreed and assigned for each activity at a sector level as the LSIP moves into the delivery phase, engagement with the providers has already commenced. has already commenced
| FOCUS | Changes Needed | ID | Activity/Tactics | Expected outcome and impact | Measure | Timing (by) | Monitoring intervals | SE | North East CA | NEAA (as designated ERB) | SSPs | ERB | Providers | Employers | DWP | Local Authorities | Social Inclusion Agencies | Schools
1. Establish a cohesive and responsive skills ecosystem that fully leverages regional excellence through aligned collaboration between providers, employers, and ERBs.
1.1 | Regional Governance | Strengthen regional co-ordination, unlock cross-sector opportunities, and enhance employer access and engagement. | 1.1.1 | Establish a Strategic Oversight Board (SOB) to oversee the delivery of the NELSIP and agree with the North East MSA the Chair and board members | Strategic Oversight Board (SOB) established with key stakeholder representation and Terms of Reference (ToR) agreed. Strong, coordinated governance of NELSIP delivery will maximise synergies across the plan by bringing together employer-led insight and strategic planning to align regional funding, enable co-designed operational mechanisms, and maintain a clear focus on SME participation in vocational training and social inclusion. | Participants agreed and meetings schedules, with conflict of interest and ToR's agreed. | July '26 | Quarterly | A | R | R | C | C | C | C | I | I | I | I
|  |  | 1.1.2 | Monitor NELSIP 26/29 deployment plan and report progress to Skills England |  | Quarterly updates on NELSIP deployment | Jul.'26 - Dec.'29 | Quarterly | A | I | R | C | C | C | C | I | I | I | I
|  |  | 1.1.3 | Establish KPIs for SME participation in vocational training in the region and embed regular reviews on progress. |  | Review Actions undertaken to improve SME participation in vocational training | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 1.1.4 | Establish a consistent set of success measures for social inclusion in education, training and employment. |  | Social inclusion success measures deployed | Sept.'26 - Dec.'29 | Quarterly | I | I | I | A | C | C | C | I | C | R | I
|  |  | 1.1.5 | Establish and monitor delivery of appropriate Level 1 and Level 2 Maths & English attainment targets - recognising value of functional equivalent qualifications where appropriate |  | Level 1 and Level 2 Maths attainment | Sept.'26 - Dec.'29 | Yearly | I | I | C | A | R | R | C | I | C | C | C
1.2 | Sector Skills Partnership (SSP) | A more consistent and scalable employer engagement system, including SMEs, is needed across the NELSIP sectors, with clearer routes into skills provision, tailored models for different sectors and supply chains, and improved communication to raise awareness, understanding and access. | 1.2.1 | Establish SSPs to support NELSIP delivery for each one of the 8 sectors and promote cross-sector collaboration. The sector ERB will act as secretariat, alongside a lead college, lead university, and key stakeholders. | An employer-led, sector-based skills system with SSPs aligned to NELSIP delivery and operating to agreed ToR - delivering a co-ordinated, simplified and responsive skills ecosystem with strong industry–provider collaboration, clear roles and accountability. This streamlined governance reduces duplication and aligns provision to current and future employer demand, whilst ensuring targeted interventions, effective access to funding, and rapid response to sector needs, including minimising workforce disruption and supporting displaced workers into priority sectors. | Participants agreed and meetings schedules, with conflict of interest and ToR's agreed. | July '26 | Yearly | I | C | A | R | C | C | C | I | I | I | I
|  |  | 1.2.2 | Each SSP will adopt a terms of reference and SHINE. |  | ToR adopted | Sept.'26 | Yearly | I | C | C | R | A | A | A | I | C | I | I
|  |  | 1.2.3 | Each SSP will sign up to SHINE |  | SHINE in place | Sept.'27 | Yearly | I | C | C | R | A | A | A | I | C | I | I
|  |  | 1.2.4 | The SSP is to agree, own and deliver sector specific priorities that feed into the overarching NELSIP - reporting outputs and outcomes to the SOB. |  | Sector deployment plan agreed, with a reporting mechanism to the Strategic Oversight Board in place. | Sept.'26 | Yearly | I | C | C | R | A | A | A | I | C | I | I
|  |  | 1.2.5 | SSPs will provide continuous assessment of employer needs and identify and report gaps. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | A | R | C | I | I | I | I
|  |  | 1.2.6 | Design and delivery of new strategic, sector-focused interventions aligned to emerging skills needs. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | A | R | C | I | I | I | I
|  |  | 1.2.7 | Identify best practice that can be shared across other SSPs |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | C | A | R | C | C | I | I | I | I
|  |  | 1.2.8 | SSP to support workforce planning and training demand, working with the sector ERB. |  | Support skills planning and visibility of the skills and priority occupations - job plan. | Sept.'26 - Dec.'29 | Yearly | I | C | R | A | R | C | C | I | I | I | I
|  |  | 1.2.9 | SSPs to assess the scale of impact and timing of AI-related workforce disruption in their sector and identify the policy, reskilling and redeployment responses required. |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | R | A | R | C | C | I | I | I | I
1.3 | Provider Collaboration | Build on NELSIF from 2023/2026 model for each sector to remove duplication and direct competition across providers for scarce specialist/technical skills required by employers. | 1.3.1 | Establish a lead college for each NELSIP sector to facilitate collaboration across FE training providers to satisfy employer demand, to share best practice, and to work with SSPs to establish new delivery models and maximise economies of scale. | A co-ordinated regional approach to specialist provision that improves viability, visibility and employer access, particularly to advanced technologies. Clear roles, responsibilities, investment priorities and areas of expertise are agreed, with shared resources maximising scarce capability and sustaining specialist, low-volume programmes. This collaborative ecosystem broadens participation in training, including SMEs, while ensuring provision is responsive to short and medium term employer skills needs. | Lead provider networks established and formally aligned to SSPs. | July'26 | Yearly | I | C | C | A | C | R | C | I | I | I | I
1.15 |  |  | 1.3.2 | Establish a lead university for each NELSIP sector to facilitate collaboration across the HE institutions to satisfy employer demand, to share best practice, to work with SSPs to establish new delivery models and maximise economies of scale. |  |  | July'26 | Yearly | I | C | C | A | C | R | C | I | I | I | I
1.16 |  |  | 1.3.3 | Lead college and lead university for each sector to drive collaboration and strengthen clearer and more coherent progression pathways. |  |  | July'26 | Quarterly | I | C | C | A | C | R | C | I | I | I | I
1.17 |  |  | 1.3.4 | Meaasure impact of provider collaboration through the "Assessing Levels of Local Skills Collaboration" matrix developed under the NELSIP 2023-2026 to ensure move towards the codetermination model. |  | Partnership agreement established and supported by in-region HE & FE providers | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | C | R | C | I | I | I | I
1.19 |  |  | 1.3.5 | Establish a region-wide network of sector focused “Centres of Excellence” that support innovation and drive adoption of advanced technologies by expanding accessible, high-level training provision, aligning funding to demand, and delivering measurable gains in workforce capability and productivity. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | R | C | C | I | C | I | I
1.4 | Funding | SSPs to drive a cohesive approach to maximise funding and delivery of employer-informed skills programmes, utilising the strengths of each organisation. | 1.4.1 | Establish sector-level plans to identify priority investment needs and optimise available public funding in support of key sector skills priorities. | A coordinated funding approach through SSPs creates a cohesive skills ecosystem, aligning and streamlining sector skills funding with NELSIP priorities. This ensures funding applications represent effective and efficient use of resources, maximises the complementary strengths of delivery partners, and optimises overall allocation and utilisation to support agreed sector outcomes | Cumulative funding secured and their relative outcome (achieved vs. target) | Sept.'26 - Dec.'29 | Quarterly | I | I | C | R | A | A | A | I | C | I | I
1.21 |  |  | 1.4.2 | Through SSPs, coordinate and pursue funding opportunities that respond to NELSIP priorities and emerging sector skills requirements, including cross-sector opportunities where appropriate. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | I | C | R | A | A | A | I | C | I | I
1.22 |  |  | 1.4.3 | Coordinate bid applications, the mobilisation, allocation and delivery of new funding opportunities that will support NELSIP delivery and any emerging sector skills requirements, maximising cross-sector opportunities in delivery and funding where possible. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | I | C | R | A | A | A | I | C | I | I
2. Enhance employability and productivity through embedded digital and AI capability
2.1 | Essential digital and AI skills | Build digital inclusivity. | 2.1.1 | Support the development of a North East MSA digital inclusion action plan that aligns to broader UK Government Digital Inclusion Action Plan Policy Paper. The plan will include the activities detailed below: | A regional digital inclusion action plan to build inclusivity and reduce barriers to employment for each of the NELSIP sectors. Close the digital divide by ensuring universal access, skills and confidence to use digital technology, delivered through locally tailored, community-based solutions. | A regional digital inclusion action plan to build inclusivity and reduce barriers to employment for each of the NELSIP sectors. Close the digital divide by ensuring universal access, skills and confidence to use digital technology, delivered through locally tailored, community-based solutions. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | R | A | A | A | C | C | C | I
2.2 |  |  | 2.1..1.1 | Skills: Build essential digital skills for work and life by providing training and support. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | A | R | C | I | I | C | I
2.3 |  |  | 2.1..1.2 | Data and device access - ensure people have devices and connectivity. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | I | I | I | C | I | C | A | R | I
2.4 |  |  | 2.1..1.3 | Accessible digital services - inclusive and easy access to public services. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | I | I | I | C | I | C | A | R | I
2.5 |  |  | 2.1..1.4 | Local support - build confidence and trust by providing community-based help locally. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | I | I | C | C | C | I | I | A | R | I
2.8 |  | Ensure basic digital and AI skills reflect the latest technologies | 2.1.2 | Review and update basic digital and AI skills in all levels of 16+ education provision. Linked to the Government's national AI pledge (£187m). | A responsive, industry-aligned digital and AI training offer that keeps pace with technological change, reduces skills decay, strengthens business resilience, improves employability, and maximises inclusive reach and funding impact. | FE Colleges provider assessment as part of the annual accountability process. For HE institutions confirmation through Access and Participation Plan. No. traineeships into jobs, graduate outcome and employability data. | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | C | C
2.9 |  |  | 2.1.3 | Design and deploy sector-focused basic digital upskilling and reskilling programmes, and utilise funding streams such as ASF and Skills Bootcamps. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | C | C
2.10 |  |  | 2.1.4 | Ensure modular delivery is available, moving from static curriculum updates to agile, bite-sized updates in keeping with the fast pace of technological change. |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | C | C
2.2 | Applied digital skills | There is an increasing requirement for hybrid digital and engineering roles to maximise productivity through process and digital optimisation. | 2.2.1 | Support cross-sector business needs for hybrid digital and engineering skills across sectors. Expand the annual attainment in HTQs and Apprenticeship (L3+) in AI/Digital framework , including Level 4 AI and Automation Practitioner apprenticeship and AI Leader modular apprenticeship units. | Accelerated digital adoption across businesses, narrowing the implementation gap and improving competitiveness. | Number of businesses participating in digital training | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.16 |  | Swiss Army – technical injection | 2.2.2 | Advanced Manufacturing: Hybrid mechatronics technicians capable of operating and maintaining Industry 4.0 – improve business productivity and efficiency. | Design clear progression pathways, increase the high-tech regional talent pool and retain technical skills in the region to support employer needs. | Number of starts, enrolments and completions in provision aligned to Advanced Manufacturing sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.17 |  |  | 2.2.3 | Offshore Wind and Renewable Energy: High-Voltage (HV) engineering with digital controls and GWO safety training, focusing on SCADA and digital grid monitoring. Training for remote monitoring and digital maintenance increases utilisation and improves productivity. |  | Number of starts, enrolments and completions in provision aligned to Offshore Wind and Renewable Energy sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.18 |  |  | 2.2.4 | Life sciences, pharmaceutical and process industries: Hybrid technicians capable of operating and maintaining Pharma 4.0 to improve business productivity and efficiency. Specific modules for digital twin bioprocessing and biologics, distinct from traditional chemical processing. |  | Number of starts, enrolments and completions in provision aligned to Life Science, Pharma and Process sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.19 |  |  | 2.2.5 | Creative Industry and Content: Develop integrated CreaTech skills pathways that combine creative and digital training across FE, HE and employer-led provision, aligned to emerging technologies and industry demand. 360-Degree Digital Creatives - Combined technical proficiencies in real-time camera/lighting layouts, rigging, sound, VFX, and post-production editing |  | Number of starts, enrolments and completions in provision aligned to Creative Industry and Content sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.20 |  |  | 2.2.6 | Construction: Digital Site Operations, use of real-time data for operational insights providing fast decision-making and improving management, including Building Information Modelling (BIM), digital job ticketing, and handheld devices. |  | Number of starts, enrolments and completions in provision aligned to Construction sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.21 |  |  | 2.2.7 | Adult Social Care: Digital Care & Telehealth - Upskill the workforce for paperless systems and remote monitoring to improve productivity. |  | Number of starts, enrolments and completions in provision aligned to Adult Social Care sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.22 |  |  | 2.2.8 | Defence, Security and Space: Secure Systems & Secure by Design: Integrate security clearance readiness and AI agents to stress-test systems against adversarial attacks. |  | Number of starts, enrolments and completions in provision aligned to Defence, Security and Space sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
|  | Modular Apprenticeship Units | 2.2.9 | Ensure modular delivery is available, moving from static curriculum updates to agile, bite-sized updates in keeping with the fast pace of technological change. For each of the NELSIP sectors, prioritise sector skills needs and plan the curriculum update/design to meet the demand. | A responsive, industry-aligned digital and AI training offer that keeps pace with technological change, reduces skills decay, strengthens business resilience, improves employability, and maximises inclusive reach and funding impact. | FE Colleges provider assessment as part of the annual accountability annual process. For HE institutions confirmation through access and participation plan. | Sept.'26 - Dec.'29 | Yearly | I | I | C | C | A | R | C | I | I | I | I
2.3 | Cyber Security | Businesses are required to be more cyber resilient due to the uptake of digital and AI technology, and the current geo-political environment. The risk of cyber disruption is now constant—and the real differentiator is not just preventing attacks but continuing to operate when they happen. | 2.3.1 | Extend basic cyber security training to those who are digitally enabled, covering data privacy, safe operation and support for digital inclusion. | Improve business resilience and reduce cyber-attack exposure | Number of people completing basic cyber security training. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.24 |  |  | 2.3.2 | Train operational cyber security specialists to support stress tests (simulating multiple cyber-attack channels to evaluate organisational resilience and recovery capabilities) and incident response. |  | Number of operational specialists completing cyber security training | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.25 |  |  | 2.3.3 | Train advanced cyber security specialists, shifting from reactive to preventative models to enforce cyber security scans and proactive remediations linked to the UK Cyber Security Council framework. |  | Number of advanced cyber security specialists. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
2.4 | Talent | Improve the region’s ability to build and sustain a strong tech talent pipeline by engaging and supporting recognised regional and national initiatives. | 2.4.1 | Support national and regional tech talent initiatives - including TechYouth (school-age tech skills and careers awareness), TechGrad (student scholarships and pathways into tech careers), TechLocal (regional employer and talent connections), and TechExpert (advanced research talent development) - to strengthen the digital talent pipeline and connect learners to regional employment opportunities. | Build and sustain the tech talent pipeline, support work-readiness and connect learners with regional employer opportunities. | No. of learners participating in regional initiatives mentioned (like TechYouth, TechGrad, TechLocal and TechExpert – Tech up, SHAREiNG, etc…). Increase the % of students progressing into digital study, training or employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | C | R | C | I | I | I | C
|  |  | 2.4.2 | Expand awareness of and participation in a range of regional initiatives. This includes TechUP, which supports learners from underserved communities; programmes in Maths and Computer Science, including the MSc in Scientific Computing and Data Analysis; and AI training through SHAREing, including Research Software Engineers; the Centre for Algorithmic Life, work exploring the relationship between human life and AI/machine learning, and AI in Schools and Education via the Centre for CPD and Outreach. NICD (National Innovation Centre for Data) Traineeships Pilot Programme (funded by DSIT), Development of comprehensive digital and AI offer,AI Academy for digital transformation of Newcastle City Council staff (phase 1 is Social Care team) |  |  | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | C | R | C | I | I | I | C
|  |  | 2.4.3 | Promote initiatives and partnerships that expand access to the work experience needed to enter technical and digital roles, including employer-led models such as Tech Talent Pro |  | Number of technical and digital work experience placements completed, and % participants progressing into technical/digital roles, apprenticeships or further training. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
3. Increase the supply of Level 3 – Level 8 technical skills to meet current and future requirements across all NELSIP sectors.
3.1 | Level 3 | Boost apprenticeship demand through employer engagement and create alternative models to mitigate the reduction of apprenticeship opportunities. | 3.1.1 | Review NELSIP 2023/26 best practice and delivery models such as AMRC, training for growth, accelerated apprenticeships and Plan Bee for each of the NELSIP sectors, with the scope to deploy new models to enhance participation. | Barriers to employer engagement in apprenticeships are reduced, enabling increased participation and a stronger alignment between apprenticeship delivery, employment opportunities and evolving market demand. | Number of L3 apprenticeships YoY. | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
|  |  | 3.1.2 | Promote T-level as entry and access to careers in the sector |  | Number of T-level learners for each of the 8 priority sectors. | Sept.'26 - Dec.'30 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.5 |  |  | 3.1.3 | Support delivery of Modular Apprenticeship Units to enrich national standard and meet employers’ L3 technical need (i.e. Electric vehicle (EV) charging point installation and maintenance — Solar PV installation and maintenance and future releases). |  | Number of L3 attainments | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.2 | Level 4/5 | Improve the lower-than-average level of L4+ attainment in the North East. | 3.2.1 | Use the Lifelong Learning Entitlement (LLE) tuition fee loan system for modular upskilling. Development of CPD programmes and apprenticeship units (where approved) | Increase progression to L4+, closing the gap between the North East and the rest of the UK. Remove systemic barriers to higher-level skills, allowing Level 2 and 3 vocational learners to progress flexibly into Higher Technical Qualifications (HTQs) and degrees. | Number of L4+ attainments | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.7 |  |  | 3.2.2 | Evaluate a flexible delivery model to support employers' requirements and widen the volume of L4/L5 opportunities. |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
|  |  | 3.2.3 | Increase and expand the availability and offer of HTQs (Higher Technical Qualifications) and degree apprenticeships. |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.8 |  |  | 3.2.4 | Utilise TECs and NEIoT to standardise and simplify the regional L4/5 offer to satisfy priority occupation (SOC20) employer demand. |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.9 |  |  | 3.2.5 | Support delivery of Modular Apprenticeship Units (Growth and Skills Levy) to enrich national standards and meet employers' technical needs (i.e. AI strategy and opportunity, AI adoption, procurement and governance, AI delivery and organisational transformation, and any future releases). |  |  | Sept.'26 - Dec.'29 | Yearly | I | C | C | C | A | R | C | I | I | I | I
3.3 | Level 6 | Improve graduate retention across the NELSIP region | 3.3.1 | Improve visibility of sector opportunities for local and non-local graduates in regional business growth clusters (CIAG). | Stronger employer-university collaboration improves graduate retention and strengthens the talent pipeline into key growth sectors. | Number of employers engaging with NELSIP Universities. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | A | R | C | I | I | I | C
3.11 |  |  | 3.3.2 | Promote graduate work experience to facilitate connection with regional employers |  | Number of graduates work placement undertaken during the academic year | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | A | R | C | I | I | I | I
3.4 | Level 7 | Low Level 7 skills attainment limits the region’s capacity to deliver innovation, leadership, and high-value growth in priority sectors. | 3.4.1 | Build regional leadership capability and promote master's-level projects to support industry innovation and productivity. | Ensure that early-stage 'blue-sky' innovations are built into technical training courses long before widespread industry demand begins. | Increase Level 7 attainment. Increase regional R&D spent | Sept.'26 - Dec.'29 | Yearly | I | C | C | A | A | R | C | I | I | I | I
|  |  | 3.4.2 | Strengthen leadership and management skills across the region to support innovation, productivity and economic growth. | Improved leadership and management capability across the region, leading to stronger workforce performance, higher productivity, and greater capacity for innovation and growth. | No. attainments in Leadership and Management training. | Sept.'26 - Dec.'29 | Yearly | I | C | C | A | A | R | C | I | I | I | I
3.5 | Level 8 | Integrate early-stage R&D funding with technical training. | 3.5.1 | Connect the region's technical education courses directly with Research England, Higher Education Innovation Funding (HEIF), and the Knowledge Exchange Framework (KEF). | More impactful research outcomes. Improved awareness of regional business innovation priorities among PhD learners, leading to stronger employer engagement and increased research collaboration. | No. of new technical education programmes linked to live R&D, innovation or knowledge exchange activity. | Sept.'26 - Dec.'29 | Yearly | I | C | I | A | R | I | C | I | I | I | I
|  |  |  | Support and promote KTPs and align employer-led blue-sky research challenges with R&D institutions. |  | No. of research challenges shared with R&D institutions. | Sept.'26 - Dec.'29 | Yearly | I | C | I | A | R | I | C | I | I | I | I
3.14 |  | Improve the understanding within R&D institutions of employer led blue sky research challenges across the NELSIP sectors. | 3.5.2 |  |  | No. of PhD learners engaged in regional employer activity. | Sept.'26 - Dec.'29 | Yearly | I | C | I | A | R | I | C | I | I | I | I
3.6 | Technical injection current and future demand | Technical injection to meet the specific skills gaps identified in the NELSIP - SSP to support future technical injection requirements. | 3.6.1 | Advanced Manufacturing including EV: Technical Skills required to pivot from traditional mechanical workflows toward automation, robotics, PLC, advanced modelling (digital twins) diagnostics. and net-zero technologies. Highly technical skills in the PEMD (Power Electronics, Machines & Drives) supply chain, battery production, and energy storage systems. Advanced diagnostics for ICE/EV systems, electronic control units (ECU), CAD, and high-integrity fabrication (MIG/TIG welding). | Design clear progression pathways to reduce/close the "Level 4 gap" and increase productivity through automation and sustainable innovation. Retain technical skills in the region to support employer need and regional projects/initiatives. (Note: Electrification and Advanced Manufacturing: Progression Pathways developed as part of the Institute of Electrification and Sustainable Advanced Manufacturing and National Battery Training and Skills Academy) Number of starts, enrolment and completion rates in Level 3+ and the % of learners progressing to higher-level training across the NELSIP sectors. | Number of starts, enrolments and completions in Level 3+ provision aligned to Advanced Manufacturing including EV sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.16 |  |  | 3.6.2 | Offshore Wind and Renewable Energy: High-Voltage (HV) electrical engineering, subsea electrical technicians, and Global Wind Organisation (GWO) safety and compliance training. Technical skills required to support Fabrication 4.0: Transitioning manual fabricators to robotic, laser, and vacuum welding specialisms. Subsea embedded systems, maritime logistics coordination, prototype engineering, and marine analytics/consenting services. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Offshore Wind and Renewable Energy sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.17 |  |  | 3.6.3 | Tech, Digital & AI: Orchestration, configuration, compliance, and governance of AI architectures and workflows (moving beyond basic prompt fluency). Providing "technical doers" for physical-digital infrastructure and support for the AI Growth Zone project - software and system engineering, complex data architecture for high-performance Graphics Processing Unit (GPU) environments, full-stack engineering, version control, and real-time 3D workflows. Advanced AI, Advanced AI with Cybersecurity; Data Science, Advanced DS with Statistics and/or specific sector needs. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Tech, Digital & AI sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.18 |  |  | 3.6.4 | Life sciences, pharmaceutical and process industries: specific requirements to support Pharma 4.0, sterile manufacturing and Good Manufacturing Practice (GMP) aseptic facility workflows, and digital twin bioprocessing/biologics. Bioinformatics, biotechnology, medicinal chemistry, biodesign, advanced organic chemistry depth (autonomous chemical synthesis), Laboratory Information Management Systems (LIMS), and advanced energy monitoring for data-intensive sterile processing. Mid-career upskilling for Qualified Persons (QPs) and senior Quality Assurance (QA) regulatory professionals. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Life Science, Pharma and Process sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.19 |  |  | 3.6.5 | Creative Industry and Content: Advanced training in Unreal Engine, virtual production volumes, motion graphics, and UI/UX wireframing. Digital marketing and audience insight; journalism, media and communication; music enterprise and industries management; creative writing and cultural content development; curating, museum and heritage practice; architecture and urban design. Freelance Readiness: Business modules covering self-employment mechanics, IR35 compliance, invoicing, and commercial workflow leadership. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Creative Industry and Content sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.20 |  |  | 3.6.6 | Defence, Security and Space: Specific sector skills include physics, data analytics, and situational awareness. Secure by Design" principles integrated across software/hardware, electronics beyond silicon, and advanced electronics R&D. Space & Orbital Analytics: Hybrid expertise spanning orbital analysis, physics, situational awareness, satellite R&D, and space law. FPGA design, signal processing for Radar/Electronic Warfare (EW), radiation-hardened circuitry, and technical clearance path preparation |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Defence, Security and Space sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.21 |  |  | 3.6.7 | Construction: PAS 2035-compliant low-carbon retrofit installation, ventilation/moisture control (damp/mould prevention), high-efficiency insulation, and low-carbon heat pump systems. Engineering programmes, covering structural, geotechnical, construction and digital engineering. Project planning, costing, scheduling, risk, foundation and structural design, surveying, BIM, spatial data and computational modelling, including finite element analysis. Level 7 study also includes offshore structures. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Construction sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
3.22 |  |  | 3.6.8 | Adult Social Care: Sustained demand for Care Workers, Training frontline staff in remote monitoring ("Virtual Wards") and digital care records to improve productivity. Domiciliary expertise in advanced pressure care, sample collection, neurodiversity tracking, and complex dementia/medication management. Upskilling senior staff to confidently navigate regulatory CQC inspections and absorb 24/7 accountability frameworks. Nursing, social work, allied health and care. |  | Number of starts, enrolments and completions in Level 3+ provision aligned to Adult Social Care sector skills requirements, and % of learners progressing into higher-level training or relevant employment. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | C | A | R | C | I | I | I | I
4. Increase SME participation in technical and vocational training
4 | Facilitate access to vocational training | Improve SME engagement and participation in the vocational skills and training offer across the NELSIP area by targeted support to overcome participation barriers, increasing demand in line with employer and sector needs. | 4.1 | Utilise ERB business networks to deploy evidence-led SME engagement approaches to improve employer understanding, access, and engagement with SME skills provision at all levels across the NELSIP area. | Improved awareness, understanding and simplified access to vocational skills provision enables greater SME participation across the region, supported by ERBs and streamlined provider processes. These drives increased uptake of training and apprenticeships whilst strengthening pathways into higher-level qualifications. A coordinated approach, shared delivery models, and sector-led best practice (including shared placements), enhances employer engagement, widens participation, and reinforces the business case for investment in skills, leading to sustained growth in apprenticeship demand and workforce capability aligned to NELSIP priorities. | Number of SMEs referred by ERBs. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.2 | Resource skills & workforce planning guidance and support for SMEs |  | Apprenticeships & training outcomes in SMEs | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.3 | Aggregate demand from SMEs across ERB networks, ensure cost-effective delivery models with practical support mechanisms to remove SME barriers. |  | Number of SMEs enrolling apprentice for the first time. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.4 | Leverage the Government's initiative and fully funded SME apprenticeships for under-25s. |  | No. of apprentices employed across SMEs in the region. | Sept.'26 - Dec.'29 | Quarterly | I | C | C | A | R | C | C | I | I | I | I
|  |  | 4.5 | Boost aggregate demand for Level 2 apprenticeship across SSPs |  | Number of Level 2 starts per year | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.6 | Develop alternative pathways to L3 apprenticeships, informed by NELSIP 2023–26 best practice paper citing AMRC, accelerated apprenticeships, training for growth and Plan Bee models. |  | Number of Level 3 apprenticeship starts within SMEs. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.7 | Promote and support initiative like Help to Grow Management Programme (Sunderland University) to SMEs in the region. |  | No. of SMEs supported through the Help to Growth Management Programme. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.8 | Utilise the centres of excellence to provide additional assistance for SMEs to recruit advanced technical apprentices requiring significant off-the-job training and on-the-job supervision. |  | SME assistance policy implemented. Apprenticeships & training starts in SMEs | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
|  |  | 4.9 | Promote case studies and success stories to SMEs of productivity and innovation improvements enabled by vocational training. |  | Apprenticeships & training starts in SMEs | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | C | C | I | I | I | I
5. Prioritise social inclusion and workforce resilience through development of foundation and employability skills, and vocational pathways into entry-level roles.
5.1 | Support for unemployed people | Improve access to employment and work-readiness by increasing the level of foundation and employability skills. | 5.1.4 | Funded work-readiness and employability assistance programmes supported by employers for those unemployed and economically inactive | Strengthen targeted and tailored support to improve employment outcomes for unemployed and economically inactive individuals, including those with special educational needs and disabilities (SEND), ensuring barriers to participation are addressed and opportunities for sustained employment are increased. | No. of economically inactive/unemployed accessing employment | Sept.'26 - Dec.'29 | Yearly | I | I | C | C | C | C | C | A | R | R | I
|  |  | 5.1.5 | Deliver tailored work-readiness and employability support programmes for under-represented groups, including people with special educational needs and disabilities. |  | Proportion of those with SEND accessing employment. | Sept.'26 - Dec.'29 | Yearly | I | I | C | C | C | C | C | A | R | R | I
5.2 | Support for Young People Pathways into Entry-Level Roles | Improve the co-ordination of employer-aligned pathways into entry-level roles. Fragmented delivery of employment support initiatives reduces effectiveness in enabling sustained re-entry into work and constrains the region’s ability to meet current and future labour market demand. | 5.2.1 | Continue to enable high-quality careers information, advice and guidance supported by North East Ambition and the deployment of Gatsby Frameworks. | Improved careers guidance, employer engagement and co-ordinated work experience, aligned to the DfE guarantee, will strengthen awareness, ambition and understanding of opportunities. This enables clearer, accessible pathways into entry-level roles and Level 2 apprenticeships, increases participation and progression through T Levels and other technical routes. This will provide better progression routes into employment or self-employment. | No. of young people receiving careers guidance | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | R | C | I | C | C | C
|  |  | 5.2.2 | Increase work experience opportunities for young people by ensuring placement brokerage is appropriately resourced and opportunities for flexible, employer-friendly placements are optimised. |  | No. of young people in education securing work-experience placements. | Sept.'26 - Dec.'29 | Yearly | I | I | C | A | R | R | C | I | C | C | C
5.8 |  |  | 5.2.3 | Promote case studies and success stories of those who have progressed through assisted pathways into entry-level roles. |  | Participation in assisted programmes | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | R | C | I | C | C | C
5.9 |  |  | 5.2.4 | SSPs to endorse different assisted pathways into entry-level roles within the sector for different populations, including those leaving education, those who are economically inactive, and those from under-represented groups including SEND. |  | Time to fill entry-level roles | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | R | C | I | C | C | C
5.10 |  |  | 5.2.5 | SSPs to endorse Level 2 apprenticeships for each sector and establish a framework of positive assistance to enable access for those who are economically inactive, or from under-represented groups including SEND. |  | Participation in Level 2 apprenticeships in key sectors | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | R | C | I | C | C | C
5.11 |  |  | 5.2.6 | Promote T Level provision as an entry route and access to careers in the STEM sectors or to employment via accelerated apprenticeships. |  | T-level attainments | Sept.'26 - Dec.'29 | Quarterly | I | I | C | A | R | R | C | I | C | C | C
5.17 |  |  | 5.2.7 | Promote aspirational case studies that inspire and demonstrate achievable career pathways for individuals from similar backgrounds. |  | Aspirational case studies promoted and engagement achieved | Sept.'26 - Dec.'29 | Quarterly | I | I | C | C | R | C | C | C | C | A | I
5.18 |  | Entrepreneurship, creativity and innovation | 5.2.8 | Widen the skills provision to support entrepreneurship, leadership, creativity and innovation. |  | Number of attainments in entrepreneurship, leadership, creativity and innovation provision. | Sept.'26 - Dec.'29 | Quarterly | I | I | C | C | A | R | C | I | I | I | I
5.3 | Employer-led | Employers proactively adopting inclusive employment practices to attract local workforce and actively supporting development of work-readiness. | 5.3.1 | ERBs and SSPs to emphasise the benefits to employers of more inclusive employment practices in a tight employment market and promote participation in SHINE. | Employers adopting more inclusive employment practices | Employer participation in SHINE | Sept.'26 - Dec.'29 | Quarterly | I | I | I | A | R | C | C | I | I | I | I
5.20 |  |  | 5.3.2 | Continued development of SHINE as a resource to employers | Progressive ongoing adoption of inclusive employment practices | Employment levels for under-represented groups | Sept.'26 - Dec.'29 | Quarterly | I | I | I | A | R | C | C | I | I | I | I
5.21 |  |  | 5.3.3 | Sponsorship of tailored sector programmes to support work-readiness, such as DWP Trailblazer, Skills Bootcamps, SWAPs and recruitment fairs. | Higher levels of employer engagement in improving work-readiness tailored to sector requirements | Conversion into employment of those attending work-readiness programmes | Sept.'26 - Dec.'29 | Quarterly | I | I | I | C | C | C | C | A | R | R | I
5.22 |  |  | 5.3.4 | Adopt a tailored approach to transitioning new employees from benefits to employment which removes financial disincentives. | Less unemployed/economically inactive residents reluctant to move into employment due to short-term risk of financial disadvantage | No. of unemployed/economically inactive accessing employment. | Sept.'26 - Dec.'29 | Quarterly | I | I | I | C | C | C | C | A | R | R | I